## Template
Title: |  | Team Members:
Date Started: | Current Date: | Executive Sponsor:
Name and Agency:
P1: Why Change is Needed |  | P4: Analysis |  |  | C7: Improvement Metrics
[6 empty] | Current | Projected | Actual
# Process Steps
# Decision Points
# Defects
# Handoffs
Lead Time
Cust Satisfaction
C8: Check Results
P2: Current State
P5: Potential Solutions
A9: Follow-up Action
P3: Goals/Targets |  | D6: Action Plan
|  | Action item | Assigned to | Due Date
Note on C5: Krall, Timothy: Why are we doing this? Why is it important? What is the business case? What is the chief complaint? (pain point, VOC) What is the impace of this issue? What is the Scope (Start and End Points)
Note on F5: Krall, Timothy: What is preventing achievement of the goal? What is the root cause or causes? Use analysis tools, 5 whys, Fishbone, pareto, etc.
Note on K14: Other results?
Note on C20: Krall, Timothy: What is happening now quantitatively? What is happening now qualitatively? Extent of the problem, facts, dates, time, frequency. Graphically present the current state.
Note on C36: Krall, Timothy: What specific outcome is required? What specifict improvements in performance are needed? Goal should be SMART( Specific, Measurable, Attainable, Relevant and Time Bound. Can be presented graphically.

## Instructions
Title: |  | Team Members:
Date Started: | Current Date: | Executive Sponsor:
Name and Agency
P1: Why Change is Needed |  | P4: Analysis |  |  | C7: Improvement Metrics
Why are we doing this? Why is it important? What is the business case? What is the chief complaint? Pain point? Customer issue? What is the impact of the issue? What is the scope - start and end points? |  | What is the gap between the current state and future state? What is preventing achievement of the goal? What is the root cause of the problem? Use problem analysis tools: fishbone diagram, 5 whys, problem analysis tree, Pareto diagram, etc .(7 quality control tools) Present a picture of the problem. |  |  |  | Current | Projected | Actual
# Process Steps
# Decision Points
# Defects
# Handoffs
Lead Time
Cust Satisfaction
C8: Check Results
What other results do you have? Include charts, graph or picture. Any $ saved? Staff time saved? Document how you calculated any savings.
P2: Current State
What is happening now quantitatively? Qualitatively? What is the extent of the problem? Use facts data, dates, times. Be visual, use charts, graphs, process map. Make the problem clear. Write a concise problem statement.
P5: Potential Solutions
Potential solutions or countermeasures. Brainstorm, evaluate, select.
A9: Follow-up Action
Evaluate the results of your improvement. What went well? What didn't go so well? Did you achieve your goal? If yes, how will you put into standard work? What issues or remaining problems can you anticipate? What's your plan for ensuring solution benefits are maintained? How will you monitor?
P3: Goals/Targets |  | D6: Action Plan
What specific outcome is required? What is the goal? The aim? State specific targets in measurable or definable terms. |  | Action item | Assigned to | Due Date
Note on C5: Krall, Timothy: Why are we doing this? Why is it important? What is the business case? What is the chief complaint? (pain point, VOC) What is the impace of this issue? What is the Scope (Start and End Points)
Note on F5: Krall, Timothy: What is preventing achievement of the goal? What is the root cause or causes? Use analysis tools, 5 whys, Fishbone, pareto, etc.
Note on K5: Graham, Racquel: Current State, Future state projection or goal. Results after a test period.
Note on K14: Other Results. Can include graphs or pictures
Note on C20: Krall, Timothy: What is happening now quantitatively? What is happening now qualitatively? Extent of the problem, facts, dates, time, frequency. Graphically present the current state.
Note on K31: Graham, Racquel:
Note on C36: Krall, Timothy: What specific outcome is required? What specifict improvements in performance are needed? Goal should be SMART( Specific, Measurable, Attainable, Relevant and Time Bound. Can be presented graphically.

## Healthcare Example
Title: Patient Transfer Process |  | Team Members:
Date Started: | Current Date: | Executive Sponsor:
Name and Agency:
P1: Why Change is Needed |  | P4: Analysis |  |  | C7: Improvement Metrics
Long delays in treatment and diagnostic procedures due to patients not being transported in a timely way creating backups in diagnostic departments, and many patient and clinician complaints. Diagnostic clinic schedules have become impossible to manage. Much time is being wasted and staff are frustrated. |  | Observed the process for 10 hours for 10 days. Average time from request to transport to delivery time in diagnostic unit is 57 minutes. Ward secretary would frequently delay calling transport due to multiple demands. Procedure department and nursing station never communicated as to expected patient transport time or procedure time. Diagnostic department inconsistent in who they called - the ward secretary, the nurse, of the transporter. Information on patient from RN or ward secretary incomplete - no room number or bed number, etc. Patients weren't always given the appropriate medication prior to a procedure. if patient not ready when transporter arrived, transporrter called the RN and left, waiting for a call back from RN. Many miscommunications. Root cause of long waits = lack of communication. |  |  | CS | FS | 30 days | 60 days | 90 days
[5 empty] | 57 min | 30 m | 14.7 m | 11 m | 11.5 m
C8: Check Results
Staff survey about satisfaction with new process. Add question to standard patient survey re: transport time for procedures.
P2: Current State
P5: Potential Solutions
Diagnostic departments will beep the Charge RN and the transporter at the same time. The page will include specific information, and a reference card. The Charge RN (or a person designated by the charge RN) and the transporter will attend the patient with specific responsibilities and make the patient aware of the ensuing procedure. Information to be included will include the name of the department, first and last name of the patient, patient medical record #, Room #, patient destination
A9: Follow-up Action
Review patient tracking sheet logs weekly for 2 months, then monthly if no issues.
P3: Goals/Targets |  | D6: Action Plan
Patient nurse, Nursing station, diagnostic department/procedure area and transport area communicate clearly and timely so that patients are ready for transport. The time from request for patient transport to delivery of patient to diagnostic or procedure area will be less than 30 minutes. |  | Action item: | Assigned to: | Due Date
|  | Develop group page | Communications & transporter | xx/xxxx
|  | Develop patient tracking sheet | trans Mgr & Nurses Betty & Sue | zz/xxxx
|  | Develop reference card with pager #s for ea charge RN | Trans Mgr & transporter Bob | yy/xxxx
|  | Standardize patient info required on reference card | Bob and Betty | yy/xxxx
|  | Standardize procedure for requesting transport | Trans Mgr | yy/xxxx
|  | Meet with clinical depts to explain new process | Trans Mgr | xx/xxxx
|  | Meet with ward secretaries to expalin new process | Trans Mgr
|  | Implement | Trans Mgr
|  | Get feedback | Trans Mgr
Note on C5: Krall, Timothy: Why are we doing this? Why is it important? What is the business case? What is the chief complaint? (pain point, VOC) What is the impace of this issue? What is the Scope (Start and End Points)
Note on F5: Krall, Timothy: What is preventing achievement of the goal? What is the root cause or causes? Use analysis tools, 5 whys, Fishbone, pareto, etc.
Note on K14: Other Results. Can include graphs or pictures
Note on C20: Krall, Timothy: What is happening now quantitatively? What is happening now qualitatively? Extent of the problem, facts, dates, time, frequency. Graphically present the current state.
Note on K27: Graham, Racquel:
Note on C36: Krall, Timothy: What specific outcome is required? What specifict improvements in performance are needed? Goal should be SMART( Specific, Measurable, Attainable, Relevant and Time Bound. Can be presented graphically.

## Training Example
Title: |  | Team Members:
Date Started: | Current Date: | Executive Sponsor:
Name and Agency
P1: Why Change is Needed |  | P4: Analysis |  |  | C7: Improvement Metrics
The plane does not fly correctly and hit a given target. The plane is not capable of consitently meeting the customer's expectations |  |  |  |  | CS | FS | 30 days | 60 days | 90 days
[5 empty] | 100% defects | 50% defects | 25% defects | 15% defects | 5 % defects
C8: Check Results
Contuinue to monitor flight times and distances to ensure that plane is performing in a controlled and capable manner. If it is not, engange in another continuout improvement initiative to ensure plane is perfoming up to the customer's standards.
P2: Current State
P5: Potential Solutions
Magnetize the target to draw the plane to it Develop a launch pad Shorten the wings Increase the stability (tape the crap out of the plane) Add landing stabilization mechanism
A9: Follow-up Action
Continue to track flight times and distances and analyze with control charts, capability analysis and regression modeling. If any of these become off target, re-conveine the team to re-asses all variables and detiemine what has changed. Continue communicating wit hthe cusomet to ensure product is meeting thier expectations.
P3: Goals/Targets |  | D6: Action Plan
Plane consistently hits target, looks awesome, accepted by customer, consistently meets expectations, is predicatable and in control |  | Action item | Assigned to | Due Date
|  | Pilot assignment | jim | today
|  | Data analysis | Lalita | 2016-10-04
|  | Fishbone creation | Alan | 2016-10-05
|  | Gather VOC | Khrista | 2016-10-06
|  | Build plane | All | 2016-10-06
Note on C5: Krall, Timothy: Why are we doing this? Why is it important? What is the business case? What is the chief complaint? (pain point, VOC) What is the impace of this issue? What is the Scope (Start and End Points)
Note on F5: Krall, Timothy: What is preventing achievement of the goal? What is the root cause or causes? Use analysis tools, 5 whys, Fishbone, pareto, etc.
Note on K12: Other Results. Can include graphs or pictures
Note on C18: Krall, Timothy: What is happening now quantitatively? What is happening now qualitatively? Extent of the problem, facts, dates, time, frequency. Graphically present the current state.
Note on K25: Graham, Racquel:
Note on C34: Krall, Timothy: What specific outcome is required? What specifict improvements in performance are needed? Goal should be SMART( Specific, Measurable, Attainable, Relevant and Time Bound. Can be presented graphically.
Voice of the customer survey, Ishikawa analysis, Design of Experiment with standardized, main effect and interaction plots, boxplots to identify the best pilots