## Instructions
Instructions for use of Integrated Plan Work Plan and Monitoring Tool
Purpose:
This Integrated Plan and Monitoring template provides jurisdictions with a dynamic tracking tool to centralize and operationalize their Integrated Plan. This is considered a "living document" that should be used to organize strategies with corresponding goals, identify data sources, delegate tasks, monitor and track progress toward goals, and support reporting.
How to use:
Jurisdictions should identify the goals and objectives outlined in the Integrated Plan and operationalize each objective with specific and measurable strategies. This information, along with measure definitions, data sources, and responsible individuals should be recorded in the respective columns. When possible, provide updates related to progress or notes relevant to the execution of the strategy.
Goal #:
Goal correspond to goals established in the 2027-2031 Integrated Plan.
Objectives | NHAS Goal | EHE Strategy | Activity/ Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2031) | Data Source | Responsible Parties | Responsible Data Staff | Responsible Program Staff | Status | Notes | Progress Notes
Objectives are actionable components of the goal and can include activities such as data gathering, programmatic activities, and meeting coordination. Multiple objectives can be included if applicable to the strategy. | Identify corresponding NHAS goal(s). | Identify corresponding EHE pillar. | Details a specific and measurable task, activity, or data point that operationalizes the objective. | Numerical value, product, or meeting convening demonstrating outcomes related to the activity. | The initial year for which future progress/outcomes will be measured against. | The initial value for which future progress/outcomes will be measured against. | The target value/outcome for the end of the IP cycle. | Where the data or outcome is tracked/stored. | Key partners involved in data collection and/or service delivery. | Office or position overseeing the collection and/or reporting of data related to the activity. | Office or position overseeing the execution/coordination of the activity. | Current state of the activity; identify any implementation barriers. | Detail information relevant to the implementation of the activity. | Details progress on activity as it relates to the overall objective; include numerical values and concrete outcomes when possible.

## Draft 2027-2031 Plan
Integrated HIV and Prevention and Care Plan Work Plan and Monitoring Table, 2027-2031 (Blue Text = Example Language from HRSA)
Goal 1: Ensure more people know their HIV status as early as possible.
Objectives | NHAS Goal | EHE Strategy | Activity/Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2031) | Data Source | Responsible Parties | Responsible Data Staff | Responsible Program Staff | Status | Notes | Progress Notes
To increase the number of rapid HIV tests conducted by 20% within the jurisdiction by 2031. | 1.2, 1.4, 2.4 | Diagnose | Increase the number of rapid HIV testing sites in under-tested (?) areas based on need identified in epidemiology data. | # of rapid HIV tests conducted | 2027 | CH- data source | baseline value + 20% | [5 empty] | Rapid HIV testing sites must conduct outreach activities/events as a condition of the MOA with FDOH. Area 7 Rapid Start Network.
To increase the number of routine HIV tests conducted by 20% within the jurisdiction by 2031. | 1.2, 1.4, 2.4 | Diagnose | Increase capacity of health care delivery systems to offer routine testing in ERs, acute care settings, urgent care, internal/primary care providers, OBGYNs, etc. | # of routine HIV tests conducted | 2027 | [7 empty] | Physician detail reporting
To increase the # of healthcare providers who provide comprehensive sexual health screening and counseling by 20% within the jurisdiction by 2031. | 1.2, 1.4, 2.4, 3.4 | Diagnose | Collaborate with local partners to educate healthcare providers on Syndemics and incorporate HIV into primary care and internal medicine practices. | # of comprehensive healthcare providers | 2027 | [7 empty] | E.g. pregnancy tests, STI panels, etc.
Goal 2: Provide medical treatment to people diagnosed with HIV within 7 days.
Objectives | NHAS Goal | EHE Strategy | Activity/Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2031) | Data Source | Responsible Parties | Responsible Data Staff | Responsible Program Staff | Status | Notes | Progress Notes
To increase the number of medical providers to include HIV medical treatment by 20% by 2031. | 2.5, 3.4, 4.1, 5 | Treat | Increase capacity of healthcare delivery systems such as ERs, acute care settings, urgent care, internal/primary care providers, OBGYNs, etc., who do not have HIV medical care available to begin providing that service. | # of medical providers who add HIV medical care | 2026
To increase capacity by 20% for medical providers to ensure treatment begins at diagnosis or most recent encounter within 7 days (Rapid Start). | 2.5, 3.4, 4.1, 5 | Treat | Assess current infrastructure to determine how to incorporate Rapid Start | # of Rapid Start programs initiated | 2026 | 29
To increase the number of PWH who are out of care that are reengaged in medical care by 20% by 2031. | 2.2, 2.3, 3.4 | Treat | 1) Identify and re-engage PWH who are out of care 2) Create and implement interventions to identify PWH who are out of care 3)To assess clinical infrastructure to determine what barriers are contributing to reengagement to care | # of out of care PWH reengaged in care | 2027 | [7 empty] | Operational definition of "out of care": PWH with no documented VL or CD4 lab, medical visit, or prescription in the previous 6 months
Goal 3: Prevent new HIV transmissions.
Objectives | NHAS Goal | EHE Strategy | Activity/Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2031) | Data Source | Responsible Parties | Responsible Data Staff | Responsible Program Staff | Status | Notes | Progress Notes
To increase the number of organizations that provide PrEP services by 30% by 2031. | 1.3, 1.4 | Prevent | Recruit and establish clinics and community-based organizations to initiate PrEP services, which include clinical prescribers and referrals. | # of organizations recruited and established |  | 29 | [6 empty] | Best practice: try to establish agreements with organizations via CTL MOAs and non-HIV providers, including ERs, acute care settings, urgent care, internal/primary care providers, OBGYNs, etc.
To expand the availability and accessibility of PrEP outside of traditional methods to priority populations by 20% by 2031. | 1.3, 1.4, 3.2 | Prevent | 1) Educate providers on cost-effectiveness and sustainable service expansion. 2) Encourage implementation of nontraditional activities with an emphasis on priority populations. | 1) # of educational sessions provided 2) # of implemented nontraditional activities 2a) # of PrEP prescriptions initiated for priority populations | [8 empty] | Priority populations are based on need identification in epidemiology data (plan-wide definition for priority populations). Availability refers to nontraditional methods include: location/venue (not in the clinic or office where services are normally provided or a non-HIV provider- see definition above), traditional office hours, holidays, and weekends. Accessibility refers to linguistically and culturally appropriate services. Include in training sessions examples of how local providers- are implementing non-traditional practices. Create a directory/list of best practices.
To increase the number of people from priority populations retained on PrEP by 20% by 2031. |  | Prevent | 1) Identify barriers and facilitators to successful PrEP persistence. | 1) # of patients persisting on PrEP | [8 empty] | Operational definition of facilitators
Insert DC language with measurable numeric lang in here |  | Prevent | Increase knowledge of HIV transmission methods and prevention techiniques. | # of programs that were designed, # of people that participate in the program, # of participants that were reached |  |  |  |  | Area 7 and 3/13 Program Office, HIP Providers
Goal 4: Example: Cluster Detection and Response (CDR) Plan
Objectives | NHAS Goal | EHE Strategy | Activity/Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2031) | Data Source | Responsible Parties | Responsible Data Staff | Responsible Program Staff | Status | Notes | Progress Notes
To develop a Cluster and Outbreak Detection and Response (CDR) Plan that can be executed effectively by 2028.A22:O23A1A22:T23A2+A22:T23 | 4.2, 4.4 | Respond | Identity and engage all key collaborators in the plan development process, including people with lived experience and those with certain risk factors for acquiring HIV | Completion of CDR Plan | 2027 |  |  | CDR Plan | CDC Recipient (HIV Prevention Coordinator), CDR Committee | HIV Prevention Coordinator | HIV Prevention Coordinator | In progress |  | Recruitment ongoing, 6 partners identified as of Q1. Meeting scheduled for Q3.
To develop a Cluster and Outbreak Detection and Response (CDR) Plan that can be executed effectively by 2028. | 4.2, 4.4 | Respond | Convene existing communities of practice to share outbreak best response practices and known gaps to guide development and key strategies in the plan | Completion of CDR Plan | 2027 |  |  | CDR Plan | CDC Recipient (HIV Prevention Coordinator), CDR Committee | HIV Prevention Coordinator | HIV Prevention Coordinator | In progress |  | First convening occurred Q1, initial report to be released Q2.
Note on B3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to confirm goal alignment is accurate
Note on A4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3 Objectives per goal/pillar. Two activities max per objective.
Note on D4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Wordsmith language around undertested/untapped areas
Note on G16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Chris H. has this data. 29 providers as of 3/5/26 Reply: 29 providers is only Area 7. Verify how many providers in Lake.
Note on N17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Create a list of operational definitions
Note on D18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Implementation goal
Note on E18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Confirm correct language

## 2022-26 Area 7-Orl. EMA IHPCP
Integrated HIV and Prevention and Care Plan Work Plan and Monitoring Table, 2022-2026
Goal 1: Prevent new HIV infections.
EHE Pillar: PREVENT
Objective 1.1 Increase HIV Awareness by 2026
Strategy 1.1.1 Develop and implement campaigns and resources to provide education about comprehensive sexual health; HIV transmission risks; options for prevention, testing, care, and treatment; and HIV-related stigma reduction.
Activity/Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2026) | Data Source | Notes (Including Responsible Data Staff & Responsible Program) | Progress Notes & Status
Increase the use of digital media resources to include messaging on dating apps (e.g., Grindr) and social media apps) | Insight data from messaging and social media sites (i.e., # of messages sent, demographic data, etc.) May need to change wording for the metrics to be more specific. | 2022 |  |  | Work with Provide to capture how clients heard about the services. Train the system on answering questions on how they heard about services. Develop a mechanism to demonstrate website traffic based launched campaigns. | Part A and subrecipients | 135,000 visits to the www.CentralFL.HIV since April 2021
Develop stigma toolkit/campaign and localized stigma task forces (survey to become part of toolkit). | # of individuals participating in stigma taskforce meetings (determined by sign-in sheets). Workplan/SOW, meeting minutes and/or agendas | 2023 |  |  |  | Peer Support Space, HIP and EHE providers | December 2022-February 2023 total of 27 participants in 3 meetings
Increase culturally competent sexual health education outside of the school systems. | # of educational sessions conducted | 2024 |  |  |  | HIP providers | Let's BeeHIVe Sista to Sista Classes 2022 total of 7 2023 total of 11 classes 2024 total of 3 classes
Increase targeted outreach and education efforts specific to specialized groups, (e.g., FQHCs, local gang taskforces, and other geographically disproportionate communities.) | # of outreach sessions conducted and types of providers participating | 2024 |  |  | Monthly progress reports to accompany monthly invoices submitted to Area 7 contract manager. | HIP and EHE providers | HIP Face to Face outreach total 200
Offer in-person learning opportunities for basic HIV 101 education and increase the number of trained HIV 101 educators. | # of classes and participants for each completing each training | 2024 |  |  |  | Areas 7 and 3/13 HIP providers | 2022 24 classes (480 participants) 2023 18 classes (360 participants) 2024 20 classes (400 Participants)
Provide HIV education and information to youth-centered outreach stakeholders to encourage buy-in and adoption of culturally competent sexual health education curriculum. | # of educational sessions conducted and types of providers participating | 2023 |  |  | Monthly progress reports to accompany monthly invoices submitted to Area 7 contract manager. | HIP and EHE providers | July-June 2023-265 youth educated through 4 educational sessions with Boys and Girls Club Downtown Orlando July-June 2024 220 youth educated through 3 educational session with the Boys and Girls Club
Strategy 1.1.2 Increase awareness of HIV among people, communities, and health workforce in disproportionately impacted areas.
Activity/Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2026) | Data Source | Notes (Including Responsible Data Staff & Responsible Program) | Progress Notes & Status
Increase targeted outreach and education efforts specific to specialized groups, (e.g., FQHCs, local gang taskforces, and other geographically disproportionate communities.) | # of outreach sessions conducted and types of providers participating | 2023 |  |  | Monthly progress reports to accompany monthly invoices submitted to Area 7 contract manager. | HIP and EHE providers | HIP Face to Face outreach total 200
Offer in-person learning opportunities for basic HIV 101 education and increase the number of trained HIV 101 educators. | # of classes and participants for each completing each training | 2024 |  |  |  | Areas 7 and 3/13 HIP providers | 2022 24 classes (480 participants) 2023 18 classes (360 participants) 2024 20 classes (400 Participants)
Provide HIV education and information to youth-centered outreach stakeholders to encourage buy-in and adoption of culturally competent sexual health education curriculum. | # of educational sessions conducted and types of providers participating | 2023 |  |  | Monthly progress reports to accompany monthly invoices submitted to Area 7 contract manager. | HIP and EHE providers | July-June 2023-265 youth educated through 4 educational sessions with Boys and Girls Club Downtown Orlando July-June 2024 220 youth educated through 3 educational session with the Boys and Girls Club
Strategy 1.1.3
Activity/Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2026) | Data Source | Notes (Including Responsible Data Staff & Responsible Program) | Progress Notes & Status
Collaborate with local partners to educate providers across multiple platforms on Syndemics and work to incorporate HIV messaging in the platforms’ communicable disease content. | # of local educational sessions conducted and # of Syndemics partners who participate | 2024 |  |  |  | RWHAP and FLDOH STI providers | Area 7 Quarterly Partner meetings total of 16 meetings (from 2022-2024)
Increase awareness and collaboration with existing SSP to incorporate hepatitis, STIs, mental health and substance abuse messaging in campaigns. | # of campaign efforts completed | 2024 |  |  |  | RWHAP and FDOH STI providers, IDEA Orlando
Objective 1.2 Increase knowledge of HIV status by 2026
Strategy 1.2.1 Test people for HIV according to the most recent USPSTF recommendations and CDC guidelines.
Activity/Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2026) | Data Source | Notes (Including Responsible Data Staff & Responsible Program) | Progress Notes & Status
Address and overcome barriers to routine HIV and other STI screening in healthcare settings and priority testing in non-healthcare settings. | # of routine HIV and STI screenings conducted in healthcare and non-healthcare settings | 2022 |  |  | Monthly progress reports to accompany monthly invoices submitted to Area 7 contract manager and STI clinic. | RWHAP and FDOH STI providers | 2023-2024 toal of 1026 STI Screenings through EHE Providers 2024-2025 total of 1026 STI Screntings through EHE Providers
Expand routine HIV and other STI testing to include additional medical settings (e.g., EDs, urgent care facilities, OB/GYNs, and PCPs) while addressing barriers. | # of routine HIV and STI screenings conducted in healthcare settings | 2023 |  |  | The monthly reports from the focus initiative | RWHAP and FDOH STI providers, acute care hospitals, healthcare systems, urgent care facilities, and community-based medical practices | Orlando Health 2023-4/23/2025 4133 tested Advent 2025
Strategy 1.2.2: Develop new and expand existing implementation of effective, evidence-based or evidence-informed models for HIV testing that improve convenience and access.
Activity/Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2026) | Data Source | Notes (Including Responsible Data Staff & Responsible Program) | Progress Notes & Status
Target testing resources to areas experiencing high transmission rates. | # of testing resources provided in ZIP Codes with high HIV infection rates | 2022 |  |  | Amend the contracts to ensure that testing location data is available. | HIV testing providers | ? define testing resource
Adopt and adapt interventions designed for populations with high exposure rates (MSM, trans people, etc.). | # of interventions adopted, # of subpopulations receiving interventions | 2022 |  |  | Monthly reports and MOU monthly reports and EHE reports | HIP, EHE, and RWHAP providers | 2023 Diva and Dialogue 29 sessions (87 participants transgender) 2024 Divas and Dialogue 24 sessions (72 participants transgender )
Continue and expand reviews of perinatal HIV transmission cases to determine how to improve systems of care. | # of case reviews conducted | 2022 |  |  | Ensure monthly reports include | Part C, TOPWA, OBGYNs, pediatricians, labor and delivery unit staff
Provide easy-to-access home test kits, including those distributed by self-serve vending machines and as add-ons to other self-administered tests (e.g., COVID-19, pregnancy). | # of HIV home test kits issued, # of HIV test kits distributed by vending machines, # of HIV test distributed as add-ons to other self-administered kits | 2022 |  |  | Monthly reports and EHE reports | FDOH Areas 7 and 3/13 (home test kits), FDOH (pregnancy and COVID tests), TOPWA | August 2022-November 2023 total of 1507 HIV home test distributed
Improve reporting structures to increase linkage to prevention, care, and treatment among people using self-administered HIV test. | # number of new policies implemented and # of existing policies updated | 2023 |  |  | Ensure monthly reports include | FDOH | ?
Strategy 1.2.3: Incorporate a status-neutral approach to HIV testing, offering linkage to prevention services for people who test seronegative and immediate linkage to HIV care and treatment for PWH.
Activity/Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2026) | Data Source | Notes (Including Responsible Data Staff & Responsible Program) | Progress Notes & Status
Develop and disseminate status multi-media neutral resources, including education materials related to HIV/STI prevention, testing, linkage, care, and treatment. (Use a multimedia approach to disseminate status neutral messaging) | # of resources developed and # disseminated | 2024 |  |  |  | FDOH | 2022 and 2023 Dear colleague letter was sent to 685 providers on Routine HIV Testing, HIV Perinatal Prevention, PrEP Access and Rapid HIV Treatment
Support informational campaigns and social media messaging around HIV/STI testing, PrEP, PEP, and linkage to care. | # of campaigns and Insight data | 2022 |  |  | Social media influencer monthly report | HIV testing providers and HIP, EHE, RWHAP providers | Jan-June 2022 total of 19 campaings (8,408,874 impressions) July-December 2022 total of 27 campaigns (9,653,262 impressions) Jan-June 2023 total of 27 campaigns (6,948,503 impressions) July-December 2023 25 campaigns (6,769,228 impressions)
Strategy 1.2.4: Provide partner services to people with HIV or other STIs and their sexual or needle-sharing partners.
Activity/Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2026) | Data Source | Notes (Including Responsible Data Staff & Responsible Program) | Progress Notes & Status
Increase the capacity of partner services by increased funding for DIS positions. | # of full-time equivalent DIS positions | 2024 |  |  |  | FDOH
Increase the capacity of partner services by conducting telehealth to conduct sessions. | # of telehealth partner sessions | 2024 |  |  |  | FDOH
Increase the capacity of partner services by expanding hours of operation. | # of partner service programs increasing their hours of operation | 2024 |  |  |  | FDOH
Use partner services to provide partners with access to PrEP and educational materials. | # of HIV seronegative partners referred to PrEP and # of HIV seronegative partners receiving educational materials | 2024 |  |  |  | FDOH
Increase the number of harm reduction programs to increase the capacity of prevention services. | # of harm reduction programs | 2024 |  |  |  | Boards of County Commissioners, RWHAP and FDOH providers, IDEA Orlando
Objective 1.3 Expand and improve implementation of effective prevention interventions from seven to ten by 2026.
Strategy: 1.3.1: Engage people at risk for HIV in traditional public health and healthcare delivery systems, as well non-traditional community settings.
Activity/Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2026) | Data Source | Notes (Including Responsible Data Staff & Responsible Program) | Progress Notes & Status
Increase the number of community mobilization initiatives and partnerships in communities (e.g., FRTA/BRTA). | # of businesses agreeing to become a FRTA/BRTA provider | 2022 |  |  |  | HIP and EHE providers | 2022 108 business agreed to become A BRTA Area 7 Program office HIP providers 2022-2024 168 toral BRTA partners
Increase collaboration with local Prevention Interventions Taskforces in raising awareness, sharing resources, and providing referrals to HIV testing (e.g., using non-healthcare events), share resources, and provide referrals. | # of collaborating taskforces and # of collaborative events | 2022 |  |  |  | EHE, HIP, and RWHAP providers | July-June 2022 total of 45 collaborating events coordinated through the following: Sistas Organizing to Survive, Talk Test Treat Latinos Taskforce and Talk Test Treat July-June 2023 total of 44 collaborating events through the following: Sistas Organizing to Survive, Talk Test Treat Latinos Taskforce and Talk Test Treat
Increase academic detailing in primary care community solo and group practices, urgent care centers, and EDs to raise awareness of HIV prevention interventions. | # of academic detailing events and # of settings in which academic detailing events are conducted | 2022 |  |  |  | RWHAP Part A, AETC, FDOH Areas 7 and 3/13 lead agencies | Area 7 physian detaling 2022-2024 336 events 4 different settings (OBGYN, Internal medicine, Primary care, urgent care centers)
Increase targeted outreach and education efforts specific to individual youth and organizations serving youth. | # of outreach and education events targeting individual youth and organizations serving youth and # of youth and teen groups receiving targeted outreach and education efforts | 2022 |  |  |  | Parts A, B, C, EHE, and HIP providers, FDOH Areas 7 and 3/13 lead agencies, Scale it Up Florida | July-June 2023-265 youth educated through 4 educational sessions with Boys and Girls Club Downtown Orlando July-June 2024 220 youth educated through 3 educational session with the Boys and Girls Club
Strategy 1.3.2: Scale-up treatment as prevention by diagnosing PWHs as early as possible and engaging them in care and treatment to achieve and sustain viral suppression.
Activity/Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2026) | Data Source | Notes (Including Responsible Data Staff & Responsible Program) | Progress Notes & Status
Expand and increase the capacity of local Rapid Access Taskforces to expand the number of rapid access programs. | # of Rapid Access providers created and # ofpeople linked through the providers | 2023 |  |  | The MOU quarterly reports. | Parts A, B, and C, EHE, and HIP providers | Number of rapid access providers as of 4/2024 17 providers through clinical MOA Number of people linked TBA
Increase the number of peers providing care and treatment support and healthcare navigation services. | # of peers employed to provide treatment support and navigation services, # of PWH receiving peer services, # of units of peer services received per PWH, % of PWH with suppressed VL, % of PWH with sustained viral suppression over time (applying HAB performance measures) | 2023 |  |  | Develop a service standard. | Parts A, B, and C, EHE, and HIP providers | EHE/Ryan White Part A employed 6 peers under two subreceipients. HIP peers 6 employed from 2023-2024 total PWH1957
Scale up HIV injectables programs. | # of injectables programs for treatment and PrEP services | 2023 |  |  | Develop a survey about the number of peers in the system and notification of when new peers are hired. | Part A, B, and C, EHE, and HIP providers, ADAP
Strategy 1.3.3: Make HIV prevention, including condoms, PrEP, PEP, SSPs easier to access and support continued use.
Activity/Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2026) | Data Source | Notes (Including Responsible Data Staff & Responsible Program) | Progress Notes & Status
Increase the number of PrEP and PEP prescribers through provision of academic detailing and education. | # of PrEP providers and # number of academic detailing activities conducted | 2022 |  |  | HIP and EHE providers, AETC
Increase the # of SSP (including clean needle distribution and exchange) statewide and ensure local sites are placed in proximity of known overdose events or deaths. | # of SSPs established and # of known overdoes | 2026 |  |  | BCC (for counties that have not implemented an SSP program), Areas 7 and 3/13 lead agencies, PART A, IDEA Orlando
Strategy 1.3.4: Implement culturally competent and linguistically appropriate models and other innovative approaches for delivering HIV prevention services.
Activity/Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2026) | Data Source | Notes (Including Responsible Data Staff & Responsible Program) | Progress Notes & Status
Provide linguistically appropriate HIV messaging in English, Spanish, and Haitian Creole. | # of HIV messages in English, Spanish, and Haitian Creole | 2022 |  |  | Parts A, B, and C, EHE, and HIP providers, Areas 7 and 3/13 lead agencies | EHE monthly reports and Part A monthly reports | 2022 World AIDS Day Messaging Spanish (95,013 insights) 2022 Puerto Rican Day Parade (125,000 insights) 2023 World AIDS Day Messaging Spanish (100,025 insights) 2023 Haitians Who Blog Women and Girls Messaging (10,000 insights) 2023 Haitians Who Blog Haitian Flag Day HIV Messaging (5,065 insights)
Increase cultural competency training workshops and other linguistically appropriate trainings for delivering HIV prevention services. | # of trainings conducted | 2024 |  |  | Part A, Part B, EHE, and HIP, providers, Areas 7 and 3/13 lead agencies, AETC |  | 2022 24 classes (480 participants) 2023 18 classes (360 participants) 2024 20 classes (400 Participants)
Engage with local and state, civic, political, community, and spiritual leaders to increase HIV awareness among populations living with or affected by HIV. | # of local, state, civic, political, and community leaders, # of spiritual leaders engaged in HIV awareness outreach sessions, and # of HIV training sessions to spiritual leaders | 2023 |  |  | Part A, Part B, EHE, and HIP, providers, Areas 7 and 3/13 lead agencies | EHE monthly reports | 2024 Area 7 engaged with 25 faith leaders session throgh 5 sessions
Goal 2: Improve HIV-related health outcomes among PWH.
EHE Pillar: DIAGNOSE
Objective 2.1 Rapidly link PWH to care after diagnosis and provide low-barrier access to HIV care and treatment.
Strategy 2.1.1 Increase linkage to HIV medical care within same day to 30 days of HIV diagnosis.
Activity/Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2026) | Data Source | Notes (Including Responsible Data Staff & Responsible Program) | Progress Notes & Status
Increase awareness among local healthcare providers by disseminating messaging on T&T and rapid ARV protocols. | # of messages on T&T and rapid ARV protocols created and distributed and # of healthcare providers receiving messages on T&T and rapid ARV protocols | 2023 |  |  |  | Part A, Part B, EHE, and HIP, providers, Areas 7 and 3/13 lead agencies | 2022 and 2023 Dear colleague letter was sent to 685 providers on Routine HIV Testing, HIV Perinatal Prevention, PrEP Access and Rapid HIV Treatment
Fund food and transportation vouchers, as well as phones to support linkage to care among PWH not in care. | # of food vouchers provided to PWH linking to care, # of transportation vouchers provided to PWH linking to care, # of phones distributed to PWH linking to care | 2023 |  |  |  | Part A, Part B, EHE, and HIP, providers, Areas 7 and 3/13 lead agencies | Area 7 EIS/Linkage from 2022-2024 900 food vouchers provided to PWH, Area 7 EIS/Linkage from 2022-2024 900 bus passes provided to PWH, Part A -Number of Unduplicated Clients who received food vouchers 2022-2023 - 490, 2023-2024 - 836, 2024-2025 - 892, Part A -Number of Unduplicated Clients who received transportation services 2022-2023 - 536, 2023-2024 - 701, 2024-2025 - 677
Expand the number of healthcare and other organizations offering T&T services including rapid access to ARVs. | # of organizations offering T&T services | 2024 |  |  |  | Part A, Part B, EHE, and HIP providers, Areas 7 and 3/13 lead agencies | Number of rapid access providers as of 4/2024 17 providers through clinical MOA Number of people linked TBA
Strategy 2.1.1 Increase linkage to HIV medical care within same day to 30 days of HIV diagnosis.
Activity/Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2026) | Data Source | Notes (Including Responsible Data Staff & Responsible Program) | Progress Notes & Status
Expand routine HIV and STI testing to additional healthcare settings (e.g., pediatricians, primary care practices, and student health centers). | # of healthcare settings providing routine HIV and STI testing. | 2024 |  |  |  | Parts A and B, EHE, and HIP, providers, Areas 7 and 3/13 lead agencies, healthcare agencies, clinicians
Objective 2.2: Identify, engage, or reengage PWH not in care or in care but not virally suppressed.
Strategy 2.2.1: Expand uptake of D2C models through data use agreements, integration data systems, and use of surveillance, clinical services, pharmacy, and social/support services data to identify and engage people not in care or not virally suppressed.
Activity/Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2026) | Data Source | Notes (Including Responsible Data Staff & Responsible Program) | Progress Notes & Status
Collaborate with local partners and providers across more platforms to incorporate more T&T facilities that will offer rapid ART and PrEP/PEP medications. | # of T&T facilities that offer rapid ART and PrEP/PEP medications | 2024 |  |  |  | Parts A and B, EHE, HIP providers, Areas 7 and 3/13 lead agencies | Area 7 physian detaling 2022-2024 336 events 4 different settings (OBGYN, Internal medicine, Primary care, urgent care centers) 2022 and 2023 Dear colleague letter was sent to 685 providers on Routine HIV Testing, HIV Perinatal Prevention, PrEP Access and Rapid HIV Treatment
Execute cooperative agreements and/or DUAs with jails, prisons, and contracting healthcare providers to link PWH before or upon released | # of cooperative agreements and/or DUAs created with jails, prisons, and contracting healthcare providers and # of recently released inmates linked to care services. | 2022 |  |  |  | Parts A, B, C, EHE, and HIP providers, Areas 7 and 3/13 lead agencies, FL DOC, County Jails
Objective 2.3: Increase retention and adherence to treatment to achieve and maintain long-term viral suppression.
Strategy 2.3.1 Develop and implement effective, evidence-based/informed interventions and support services that improve retention in care.
Activity/Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2026) | Data Source | Notes (Including Responsible Data Staff & Responsible Program) | Progress Notes & Status
Collaborate with local partners to educate healthcare providers on Syndemics and incorporate HIV into primary care and internal medicine practices. | # of providers trained, # of primary care practices that incorporate routine HIV care, | 2023 |  |  |  | Parts A and B, EHE, and HIP providers, Areas 7 and 3/13 lead agencies, medical practices, AETC | Area 7 physian detaling 2022-2024 336 events 4 different settings (OBGYN, Internal medicine, Primary care, urgent care centers) 2022 and 2023 Dear colleague letter was sent to 685 providers on Routine HIV Testing, HIV Perinatal Prevention, PrEP Access and Rapid HIV Treatment
Expand peer linkage and Community Health Workers (CHWs) to implement Anti-Retroviral Treatment and Access to Services (ARTAS) intervention strategies and adherence measures. | # of peers and CHWs trained and # of CHWs certified | 2022 |  |  |  | Parts A and B, EHE, and HIP providers, Areas 7 and 3/13 lead agencies, certification programs | total of 2 peers supporting the ARTS program from 2022-2025
Goal 3: Reduce HIV-related disparities and health inequities.
EHE Pillar: TREAT
Objective 3.1 Reduce HIV-related stigma and discrimination
Strategy 3.1.1 Ensure that healthcare professionals and front-line staff complete education and training on stigma, discrimination, and unrecognized bias toward populations with or at risk for HIV.
Activity/Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2026) | Data Source | Notes (Including Responsible Data Staff & Responsible Program) | Progress Notes & Status
Identify and disseminate continuing education opportunities and training for healthcare professionals and front-line workers on HIV stigma. | # of materials or resources created and # of materials or resources distributed | 2023 |  |  |  | Parts A and B, EHE, and HIP, providers, Areas 7 and 3/13 lead agencies, AETC, Area Health Education Centers (AHEC)
Work with professional organizations to encourage the adoption of HIV stigma training as part of professional standards for healthcare professionals and front-line staff. | # of stigma trainings conducted, # of trainees, # of professional organizations that adopt HIV stigma training | 2023 |  |  |  | Part A, Part B, EHE, and HIP, providers, Areas 7 and 3/13 lead agencies, AETC, local medical society chapters
Strategy 3.1.2 Ensure HIV educational resources are focused on the communities and populations where the need is greatest (e.g., Black, Hispanic/Latino, American Indian/Alaska Native, and other people of color, gay and bisexual men, transgender people, people who use substances, sex workers, and immigrants).
Activity/Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2026) | Data Source | Notes (Including Responsible Data Staff & Responsible Program) | Progress Notes & Status
Create and/or adopt informational materials focusing on communities and population where the need is greatest. | # of informational materials created or adopted | 2023 |  |  |  | Parts A, B, EHE, and HIP providers, Areas 7 and 3/13 lead agencies, AETC
Support ongoing and new initiatives and programs specifically focused on communities and populations where the need is greatest. | # of new initiatives funded and # of established programs funded | 2023 |  |  |  | Parts A, B, EHE, and HIP providers, Areas 7 and 3/13 lead agencies, AETC, CBOs
Increase the number of mobile medical units and street outreach to bring services and resources to communities and populations where the need is greatest. | # of people receiving outreach encounters (e.g., HIV testing, materials, etc.) | 2022 |  |  |  | Parts A, B, EHE, and HIP providers, Areas 7 and 3/13 lead agencies, AETC, CBOs | From 2022 to current there are a total of 20 service providers have mobile medical units
Objective 3.2 Reduce disparities in new HIV infections, awareness of HIV status, and along the HIV Care Continuum
Strategy 3.2.1 Increase awareness of HIV-related disparities in the OSA through data collection, analysis, and dissemination of findings.
Activity/Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2026) | Data Source | Notes (Including Responsible Data Staff & Responsible Program) | Progress Notes & Status
Develop and/or expand the use of easy-to-read materials (e.g., infographics, one-pagers) to help audiences of varying types (e.g., the public, PWH, providers) to highlight disparities. | # of materials created and/or adopted | 2022 |  |  |  | Part A, Part B, EHE, and HIP providers, Areas 7 and 3/13 lead agencies
Expand the use of data dashboards and provide education to relevant groups on how to access and use the information to increase awareness of HIV-related disparities. | # of data dashboards created and # of individuals using the data dashboards | 2024 |  |  |  | Part A | Data dashboard created for EHE initiatives (Jail Linkage and Community Testing Linkage)
Objective 3.3: Address social determinants of health and co-occurring conditions that contribute to HIV-related disparities.uce disparities in new HIV infections, awareness of HIV status, and along the HIV Care Continuum
Strategy 3.3.1 Adopt policies that reduce barriers to improving accessibility of clinical and support services for PWH.
Activity/Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2026) | Data Source | Notes (Including Responsible Data Staff & Responsible Program) | Progress Notes & Status
Create consistencies (e.g., longer time between recertification, reciprocal eligibility) within the RWHAP-funded care system to eliminate barriers to HIV care. | # of new policies and procedures that ensure consistency and efficiency in RWHAP enrollment and redetermination | 2022 |  |  |  | Parts A and B | Reciprical eligibility established November 2022
Explore the incorporation of afterhours and weekend services for PWH to promote retention in care and adherence to treatment. | # of HIV care and support service agencies providing after hours and/or weekend services | 2022 |  |  |  | Parts A and B, Areas 3 and 3/13 lead agencies | From 2022 to current there are a total of 20 service providers who provide HIV care and support services after hours/weekends
Goal 4: Achieve integrated, coordinated efforts among all partners and interested parties who wish to address the HIV epidemic.
EHE Pillar: RESPOND
Objective 4.1 Integrate programs to address the Syndemics of HIV, STIs, viral hepatitis and substance use and mental health disorders in the context of social and structural/institutional factors including stigma, discrimination, and violence.
Strategy 4.1.1 Integrate HIV awareness and services into outreach and services for issues that intersect with HIV such as intimate partner violence, homelessness, housing instability, STIs, viral hepatitis, and substance abuse/mental health disorders.
Activity/Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2026) | Data Source | Notes (Including Responsible Data Staff & Responsible Program) | Progress Notes & Status
Expand marketing and advertising campaigns of internal and external partners to promote increased awareness of resources and services. | # of advertising campaigns created and # of internal and external partners participating in marketing and advertising campaigns | 2022 |  |  |  | Parts A and EHE, and HIP providers, Areas 7 and 3/13 lead agencies
Increase partnerships with providers to conduct mobile HIV awareness and services. | # of partnerships created with providers that conduct mobile services | 2022 |  |  |  | Parts A and EHE, and HIP providers, Areas 7 and 3/13 lead agencies | From 2022 to current there are a total of 20 service providers have mobile medical units
Use social media and outreach to disseminate program results and success stories. | # of success stories and program results disseminated via social media | 2022 |  |  |  | Parts A and EHE, and HIP providers, Areas 7 and 3/13 lead agencies
Objective 4.2 Enhance the quality, accessibility, dissemination, and application of aggregate data and analytic analyses, including data regarding HIV prevention and care continuum and social determinants of health.
Strategy 4.2.1 Promote collection, electronic sharing, and use of HIV risk, prevention, care, and treatment data using interoperable data standards, including data from EHRs, in accordance with applicable federal and FL law.
Activity/Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2026) | Data Source | Notes (Including Responsible Data Staff & Responsible Program) | Progress Notes & Status
Create a centralized system or dashboard to disseminate aggregate HIV-related data (e.g., testing, treatment, surveillance) internally and externally that can be readily used to assess local area disease burden, obtain information needed for funding requests, and data required for time sensitive action and response. | # of data dashboards created and # of DUAs established | 2023 |  |  |  | Part A | Data shared in www.CentralFL.HIV
Collaborate with FDOH to create a reciprocal client informed consent form and release of information to acknowledge that data may be shared to improve service provision, linkage, and retention services. | # of policies and procedures developed to create a reciprocal client informed consent and release of information | 2022 |  |  |  | Parts A, B, C and FDOH | Data Sharing Consent established 2022